## Master
Indian Waters Council Recruitment Event Backdater
Enter Name of Event Here |  | Event Date | 2026-06-01
Enter Event Location Here
Unit Leader | Enter Contact Number
Unit New Member Coordinator | Enter Contact Number
Unit Commissioner | Enter Contact Number
District Membership Chair | Enter Contact Number
District Staffing Professional | Enter Contact Number
TASK - Backdates are considered completion dates | Assigned To | DAYS OUT FROM EVENT | DUE DATE | What Do I need to do? Where Can I find this? | URGENCY | Progress
Complete unit membership plan and review with your Unit Commissioner and/or District Membership Chair |  | 30 | 2026-05-02
Submit unit membership plan to Council through your District Staffing Professional |  | 30 | 2026-05-02
Check your BeAScout pin and make sure information is correct |  | 29 | 2026-05-03
Reserve location for your event - typically at a local school or your meeting location |  | 28 | 2026-05-04
Contact school principal for approval to send home flyers (some may prefer electronic flyers) |  | 28 | 2026-05-04
Secure date of your school's open house. Contact school to request a table. This is to promote your joining night, not replace it! |  | 24 | 2026-05-08
Submit Geo-fencing/Facebook ad request to Council |  | 24 | 2026-05-08
Submit customized flyer request (electronic or hard copy) |  | 23 | 2026-05-09
Finalize unit's 2026-2027 program calendar and fees |  | 16 | 2026-05-16
Plan your Join Scouting Night agenda with unit leaders |  | 16 | 2026-05-16
Submit customized yard sign/poster request |  | 13 | 2026-05-19
Deliver approved full-sheet flyers to school |  | 13 | 2026-05-19
Ask school to post flyer to social media and/or website (if they sent home hard copy flyers) |  | 12 | 2026-05-20
Post to commmunity online groups, Facebook pages |  | 12 | 2026-05-20
Deliver extra flyers/posters to places kids and families frequent |  | 12 | 2026-05-20
Get your charter organization involved and post to their social media, website, newsletter or bulletin |  | 12 | 2026-05-20
Hang flyers on community announcement boards |  | 12 | 2026-05-20
Ask parents who are on Facebook, LinkedIn, Instagram, Nextdoor, etc. to update their status to talk about your unit's Joining Night |  | 10 | 2026-05-22
Ask parents in your pack to send an email invitation to all of their friends that have Scout-age youth. People like to join organizations where they know other people. |  | 8 | 2026-05-24
Send youth in your Pack home with Peer to Peer cards to hand out to their friends |  | 8 | 2026-05-24
Review your Joining Night agenda/plan and make any necessary changes |  | 8 | 2026-05-24
Council with publish customized Facebook ad for your event |  | 8 | 2026-05-24
Place yard signs in targeted locations |  | 6 | 2026-05-26
Remind parents to send emails/youth to hand out peer to peer cards |  | 6 | 2026-05-26
Final review of Joining Night agenda with unit leaders |  | 4 | 2026-05-28
Print unit QR code for online application |  | 4 | 2026-05-28
Confirm All Supplies on hand for Event Date |  | 2 | 2026-05-30
Final Sharing to Social Media Groups |  | 1 | 2026-05-31
Successfully Host Event |  | 0 | #VALUE!
Assessment & Collected Data Organization |  | 1 | 2026-06-02
Follow up with Newly Registered Scouts |  | 2 | 2026-06-03
Follow up with Families that have not yet registered to invite them to your next unit meeting |  | 3 | 2026-06-04
Formulas:
DUE DATE = D2-[DAYS OUT FROM EVENT]
DUE DATE = D2+[DAYS OUT FROM EVENT]